## Defects
Sl. No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Anagha S | 2026-09-03 | Duplicate search results were displayed when the same document was processed multiple times. | Sprint 1 | Anagha S | Logical | Implemented stable document source identification and session-based file processing to prevent repeated indexing. | 2026-09-03 | Closed | Issue resolved and semantic search results are now displayed without unintended duplicates.
2 | Anagha S | 2026-09-03 | HTML formatting appeared as plain markup in the Streamlit search results. | Sprint 1 | Anagha S | User Interface | Replaced HTML-based result rendering with native Streamlit components such as st.markdown() and st.write(). | 2026-09-03 | Closed | Search results are now displayed correctly in a readable format.
3 | Anagha S | 2026-09-03 | PDF test execution initially failed because the test file did not contain a valid PDF header. | Sprint 1 | Anagha S | Logical | Replaced the invalid test PDF with a valid PDF test file and verified the PDF loader again. | 2026-09-03 | Closed | PDF ingestion test executed successfully after correction.
4 | Anagha S | 2026-09-03 | DOCX loader test initially encountered an execution error. | Sprint 1 | Anagha S | Logical | Corrected the DOCX loader/test implementation and reran the test successfully. | 2026-09-03 | Closed | DOCX document extraction is working correctly.
5 | Anagha S | 2026-09-03 | Streamlit application initially reported a missing torchvision dependency. | Sprint 1 | Anagha S | Others | Installed the required torchvision package and verified the embedding model execution. | 2026-09-03 | Closed | Embedding model and Streamlit application run successfully.
1 | Anagha S | 2026-09-10 | Multi-document upload was not initially supported in the project workflow. | Sprint 2 | Anagha S | Functional | Implemented multi-document upload and processing through the Streamlit interface. | 2026-09-10 | Closed | Multi-file project analysis enabled.
2 | Anagha S | 2026-09-11 | Retrieval results could include irrelevant information when multiple project documents were selected. | Sprint 2 | Anagha S | Retrieval | Refined source handling and updated the RAG search logic for document retrieval. | 2026-09-11 | Closed | Improved relevance of retrieved project evidence.
3 | Anagha S | 2026-09-12 | Scope Agent generated unnecessary text instead of structured project information. | Sprint 2 | Anagha S | AI Output | Updated the Scope Agent with structured extraction instructions and section-specific retrieval. | 2026-09-12 | Closed | Scope output structured into goals, deliverables, milestones, timeline and responsibilities.
4 | Anagha S | 2026-09-13 | Risk and blocker analysis required better evidence-based project information. | Sprint 2 | Anagha S | AI Analysis | Refined Risk Agent and Blocker Agent to use project dependencies, blockers and action items as evidence. | 2026-09-14 | Closed | Risk and blocker analysis integrated into the project intelligence workflow.
5 | Anagha S | 2026-09-15 | AI analysis required integration into a single project intelligence interface. | Sprint 2 | Anagha S | Integration | Integrated Scope, Risk and Blocker Agents into the Streamlit dashboard. | 2026-09-15 | Closed | Milestone 2 integrated dashboard prepared for demonstration.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others