PROJECT MEETING NOTES

Project: E-Commerce Platform Modernization

Meeting Date: September 15, 2026

Meeting Type: Weekly Project Status Meeting

Project Status

The project is currently progressing through the architecture and initial development activities. The cloud architecture design has been completed. Product catalog migration has started, and the authentication module is currently under development.

Completed Activities

• Cloud architecture design completed by Ananya.

• Initial product catalog migration started.

• CI/CD pipeline design has been discussed.

• Integration testing plan has been prepared by the QA team.

Current Issues

The payment gateway integration is currently blocked because the required payment provider credentials have not yet been received.

The authentication module is still under development and must be completed before system integration testing can begin.

The cloud environment requires final infrastructure approval before production deployment.

Key Dependencies

• Payment gateway integration depends on receiving payment provider credentials.

• System integration testing depends on completion of the product catalog and authentication modules.

• Production deployment depends on successful integration testing and cloud environment approval.

Decisions Made

1. System integration testing will remain scheduled for October 21, 2026.

2. Payment gateway integration will begin immediately after the required provider credentials are received.

3. The QA team will prepare test cases in parallel while development activities continue.

Action Items

1. Arjun will follow up on the payment provider credentials by September 18, 2026.

2. Meera will complete the authentication module by October 15, 2026.

3. Rahul will continue product catalog migration and target completion by October 5, 2026.

4. Ananya will coordinate the final cloud infrastructure approval.

5. Karthik will continue CI/CD pipeline implementation with a target completion date of October 25, 2026.

6. The QA team will finalize integration test cases before October 21, 2026.

Next Review

The next project status review will evaluate payment gateway credentials, authentication progress, product catalog migration, and cloud infrastructure approval.